## OVERVIEW
Database | Data Migração | Origem | Apps (experian-*-domain-services/webhook) | Source EC2 Cluster | Target DocumentDB cluster | Target Digital EC2 cluster | Actual Volume (MB) | Business criticality | Status | Obs
account | 2023-05-03 | EC2 | account, account-event-payload, account-webhook, organization-structure, services-account | account-iam | docdb-account-services | mongodb-account-iam | 222747 | 1- Highly Critical | Not migrated
iam | 2023-05-04 | EC2 | iam, iam-batch, iam-event-payload, iam-legacy, identity-migration | account-iam | docdb-account-services | mongodb-account-iam | 3595350 | 1- Highly Critical | Not migrated
leadinfo | 2023-04-19 | EC2 | enrichment | customer-relationship | docdb-account-services | mongodb-account-iam | 36864 | 2- Critical | Migrated | Verificar nome mais semantico / lead-enrichment-batch não é feito deploy, alterar uri do job no Rundeck
marketingAutomation | 2023-04-11 | DocumentDB | marketing-builder,marketing-consumer |  | docdb-account-services | mongodb-account-iam | 2048 | 3 - Medium | Migrated
catalogue | 2023-04-11 | DocumentDB | catalogue | customer-relationship | digital-commerce-services | mongodb-digital-commerce-services | 1 | 2- Critical | Migrated
checkout | 2023-05-02 | EC2 | checkout-management | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 820 | 4- Low | Migrated
marketingcampaign | 2023-04-26 | EC2 | marketing-campaign | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 7064 | 2- Critical | Migrated
orderbalance | 2023-04-27 | EC2 | order-balance | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 5060 | 2- Critical | Migrated
orderBalanceWebhook | 2023-04-24 | EC2 | order-balance-webhook | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 1 | 3 - Medium | Migrated
ordersession | 2023-04-25 | EC2 | order-session-batch, order-session-management, order-session-notification-consumer | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 96256 | 2- Critical | Migrated
orderSessionWebhook | 2023-04-27 | EC2 | order-session-webhook | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 565 | 2- Critical | Migrated
payment | 2023-05-02 | EC2 | payment | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 1 | 2- Critical | Migrated | Não foi encontrada a aplicação no ambiente produtivo para fazer a troca da string de conexão
quartz | 2023-04-24 | EC2 | order-session-batch | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 7168 | 3 - Medium | Migrated
salesFraudScreening | 2023-05-02 | EC2 | fraud-screening-job, sales-fraud-screening | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 168245 | 2- Critical | Migrated
shoppingcart | 2023-05-02 | EC2 | shopping-cart-management | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 2582 | 4- Low | Migrated
showcase | 2023-05-10 | EC2 | showcase-management | digital-commerce-services | digital-commerce-services | mongodb-digital-commerce-services | 888788 | 2- Critical | Not migrated
emailValidation | 2023-04-25 | EC2 | email-validation | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 8192 | 2- Critical | Migrated
kba | 2023-04-12 | DocumentDB | kba | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 3 | 4- Low | Migrated | Banco vazio
personValidation | 2023-04-18 | EC2 | person-validation | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 37 | 4- Low | Migrated
phoneValidation | 2023-04-19 | EC2 | phone-validation | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 647 | 2- Critical | Migrated
validation | 2023-04-12 | DocumentDB | validation | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 8 | 2- Critical | Migrated | Renomeado para validation
verifyid | 2023-04-18 | EC2 | verifyid | customer-relationship | digital-kyc-services | mongodb-digital-kyc-services | 46 | 4- Low | Migrated
adChanges | 2023-04-26 | EC2 | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | account-iam | digital-security-services | mongodb-digital-security-services | 8784 | 4- Low | Migrated
crypto | 2023-04-19 | EC2 | crypto-consumer, crypto | digital-services-crypto | digital-security-services | mongodb-digital-security-services | 21504 | 3 - Medium | Migrated
device | 2023-05-10 | EC2 | device | customer-relationship | digital-security-services | mongodb-digital-security-services | 1654982 | 1- Highly Critical | Not migrated
digitalCertificateWebhook | 2023-04-25 | EC2 | digital-certificate-webhook | account-iam | digital-security-services | mongodb-digital-security-services | 1 | 4- Low | Migrated
digitalKms | 2023-04-12 | DocumentDB | digital-kms | customer-relationship | digital-security-services | mongodb-digital-security-services | 1 | 4- Low | Migrated
iamSaml | 2023-04-26 | EC2 | iam-saml-integration | account-iam | digital-security-services | mongodb-digital-security-services | 1 | 3 - Medium | Migrated | Base com views, migrada com dump/restore
otp | 2023-04-24 | EC2 | otp | account-iam | digital-security-services | mongodb-digital-security-services | 897 | 4- Low | Migrated
policy | 2023-04-12 | DocumentDB | policy, policy-settings | customer-relationship | digital-security-services | mongodb-digital-security-services | 1 | 4- Low | Migrated | Banco vazio, apps em descomissionamento
vault | 2023-04-26 | EC2 | vault | mongodb-digital-services |  | mongodb-digital-security-services |  | 2- Critical | Migrated | Forkar collections do vault de dentro do sendgrid
drive | 2023-04-27 | EC2 | drive, drive-transfer | customer-relationship | digital-services | mongodb-digital-services | 9665 | 1- Highly Critical | Migrated
driveWebhook | 2023-04-18 | DocumentDB | driveWebhook | customer-relationship | docdb-digital-services | mongodb-digital-services | 1 | 4- Low | Migrated | Base vazia, só criar a base no document e mudar a string
emailCommunication | 2023-04-25 | DocumentDB | email-communication | customer-relationship | digital-services | mongodb-digital-services |  | 2- Critical | Migrated | Base vazia, só criar a base no destino
healthcheck | 2023-04-27 | DocumentDB |  |  | docdb-digital-services | mongodb-digital-services |  | 4- Low | Migrated
notification | 2023-04-18 | DocumentDB | notification, notification-settings | digital-notification | docdb-digital-services | mongodb-digital-services | 2048 | 3 - Medium | Migrated
platform | 2023-04-24 | DocumentDB | product-platform | digital-products | docdb-digital-services | mongodb-digital-services | 102 | 1- Highly Critical | Migrated
product | 2023-04-26 | DocumentDB | product-access | digital-products | docdb-digital-services | mongodb-digital-services | 4242 | 1- Highly Critical | Migrated | Avaliar possibilidade de um cluster "mongodb-digital-product-services" para o Atlas
productMenuSecurity | 2023-04-26 | DocumentDB | product-menu-security | digital-products | docdb-digital-services | mongodb-digital-services | 182 | 1- Highly Critical | Migrated | Avaliar possibilidade de um cluster "mongodb-digital-product-services" para o Atlas
sendgrid | 2023-04-11 | EC2 | email-communication-webhook, sendgrid, vault | persona-video-loan | digital-services | mongodb-digital-services | 32768 | 2- Critical | Migrated
sms | 2023-04-25 | EC2 | sms, sms-webhook | customer-relationship | digital-services | mongodb-digital-services | 230 | 2- Critical | Migrated
switching | 2023-04-27 | EC2 | switching | customer-relationship | docdb-digital-services | mongodb-digital-services | 51 | 1- Highly Critical | Migrated | Validar indices das collection
callcenter |  | DocumentDB |  | customer-relationship | backup to Glacier and delete | N/A | 324 | 3 - Medium | Won't migrate
consultafacil |  | DocumentDB |  | digital-commerce-services | delete | N/A |  | - | Won't migrate
consultafacilreports |  | DocumentDB |  | digital-commerce-services | delete | N/A |  | - | Won't migrate
consultafacilsecurity |  | DocumentDB |  | digital-commerce-services | delete | N/A |  | - | Won't migrate
dacourses |  | DocumentDB |  | digital-commerce-services | backup to Glacier and delete | N/A |  | - | Won't migrate
iamlegacy |  | DocumentDB |  | customer-relationship | delete | N/A |  | - | Won't migrate
partner |  | DocumentDB |  | account-iam | delete | N/A |  | 4- Low | Won't migrate
userqrcode |  | DocumentDB |  | customer-relationship | backup to Glacier and delete | N/A |  | - | Won't migrate
wallet |  | DocumentDB | wallet | customer-relationship | backup to Glacier and delete | N/A | 47 | 4- Low | Won't migrate

## Mongo > Atlas - DEV
Database | Apps (experian-*-domain-services/webhook) | Target Digital EC2 cluster | EKS NameSpace | Actual Volume (MB) | Business criticality | Ordem | Ordem Nova | Data UAT | Data Prod
kba | kba | mongodb-digital-kyc-services | digital-kyc-services-dev | 3 | 4- Low | 1
personValidation | person-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 37 | 4- Low | 1
verifyid | verifyid | mongodb-digital-kyc-services | digital-kyc-services-dev | 46 | 4- Low | 1
digitalCertificateWebhook | digital-certificate-webhook | mongodb-digital-security-services | digital-identity-services-dev | 1 | 4- Low | 1
adChanges | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | mongodb-digital-security-services | digital-security-services-dev | 8784 | 4- Low | 2
digitalKms | digital-kms | mongodb-digital-security-services | digital-security-services-dev | 1 | 4- Low | 2
otp | otp | mongodb-digital-security-services | digital-security-services-dev | 897 | 4- Low | 3
policy | policy, policy-settings | mongodb-digital-security-services | DESCONTINUADO | 1 | 4- Low | 3
driveWebhook | driveWebhook | mongodb-digital-services | digital-storage-services-dev | 1 | 4- Low | 3
healthcheck |  | mongodb-digital-services | digital-services-dev |  | 4- Low | 3
crypto | crypto-consumer, crypto | mongodb-digital-security-services | digital-security-services-dev | 21504 | 3 - Medium | 4
iamSaml | iam-saml-integration | mongodb-digital-security-services | digital-identity-services-dev | 1 | 3 - Medium | 4
notification | notification, notification-settings | mongodb-digital-services | digital-product-services-dev | 2048 | 3 - Medium | 4
marketingAutomation | marketing-builder,marketing-consumer | mongodb-account-iam | digital-account-services-dev | 2048 | 3 - Medium | 4
emailValidation | email-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 8192 | 2- Critical | 5
phoneValidation | phone-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 647 | 2- Critical | 5
validation | validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 8 | 2- Critical | 5
vault | vault | mongodb-digital-security-services | digital-security-services-dev |  | 2- Critical | 6
leadinfo | enrichment | mongodb-account-iam | digital-account-services-dev | 36864 | 2- Critical | 6
emailCommunication | email-communication | mongodb-digital-services | digital-communication-services-dev |  | 2- Critical | 7
sendgrid | email-communication-webhook, sendgrid, vault | mongodb-digital-services | digital-communication-services-dev | 32768 | 2- Critical | 7
sms | sms, sms-webhook | mongodb-digital-services | digital-communication-services-dev | 230 | 2- Critical | 7
platform | product-platform | mongodb-digital-services | digital-product-services-dev | 102 | 1- Highly Critical | 8
productMenuSecurity | product-menu-security | mongodb-digital-services | digital-product-services-dev | 182 | 1- Highly Critical | 8
switching | switching | mongodb-digital-services | digital-product-services-dev | 51 | 1- Highly Critical | 8
device | device | mongodb-digital-security-services | digital-security-services-dev | 1654982 | 1- Highly Critical | 9
drive | drive, drive-transfer | mongodb-digital-services | digital-storage-services-dev | 9665 | 1- Highly Critical | 9
product | product-access | mongodb-digital-services | digital-product-services-dev | 4242 | 1- Highly Critical | 9
account | account, account-event-payload, account-webhook, organization-structure, services-account | mongodb-account-iam | digital-account-services-dev | 222747 | 1- Highly Critical | 10
iam | iam, iam-batch, iam-event-payload, iam-legacy, identity-migration | mongodb-account-iam | digital-identity-services-dev | 3595350 | 1- Highly Critical | 11
catalogue | catalogue | mongodb-digital-commerce-services |  | 1 | 2- Critical | PME - DocumentDB
checkout | checkout-management | mongodb-digital-commerce-services |  | 820 | 4- Low | PME - DocumentDB
marketingcampaign | marketing-campaign | mongodb-digital-commerce-services |  | 7064 | 2- Critical | PME - DocumentDB
orderbalance | order-balance | mongodb-digital-commerce-services |  | 5060 | 2- Critical | PME - DocumentDB
orderBalanceWebhook | order-balance-webhook | mongodb-digital-commerce-services |  | 1 | 3 - Medium | PME - DocumentDB
ordersession | order-session-batch, order-session-management, order-session-notification-consumer | mongodb-digital-commerce-services |  | 96256 | 2- Critical | PME - DocumentDB
orderSessionWebhook | order-session-webhook | mongodb-digital-commerce-services |  | 565 | 2- Critical | PME - DocumentDB
payment | payment | mongodb-digital-commerce-services |  | 1 | 2- Critical | PME - DocumentDB
quartz | order-session-batch | mongodb-digital-commerce-services |  | 7168 | 3 - Medium | PME - DocumentDB
salesFraudScreening | fraud-screening-job, sales-fraud-screening | mongodb-digital-commerce-services |  | 168245 | 2- Critical | PME - DocumentDB
shoppingcart | shopping-cart-management | mongodb-digital-commerce-services |  | 2582 | 4- Low | PME - DocumentDB
showcase | showcase-management | mongodb-digital-commerce-services |  | 888788 | 2- Critical | PME - DocumentDB

## Mongo > Atlas - QA
Database | Apps (experian-*-domain-services/webhook) | Target Digital EC2 cluster | EKS NameSpace | Actual Volume (MB) | Business criticality | Ordem | Ordem Nova | Data UAT | Data Prod
kba | kba | mongodb-digital-kyc-services | digital-kyc-services-dev | 3 | 4- Low | 1
personValidation | person-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 37 | 4- Low | 1
verifyid | verifyid | mongodb-digital-kyc-services | digital-kyc-services-dev | 46 | 4- Low | 1
digitalCertificateWebhook | digital-certificate-webhook | mongodb-digital-security-services | digital-identity-services-dev | 1 | 4- Low | 1
adChanges | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | mongodb-digital-security-services | digital-security-services-dev | 8784 | 4- Low | 2
digitalKms | digital-kms | mongodb-digital-security-services | digital-security-services-dev | 1 | 4- Low | 2
otp | otp | mongodb-digital-security-services | digital-security-services-dev | 897 | 4- Low | 3
policy | policy, policy-settings | mongodb-digital-security-services | DESCONTINUADO | 1 | 4- Low | 3
driveWebhook | driveWebhook | mongodb-digital-services | digital-storage-services-dev | 1 | 4- Low | 3
healthcheck |  | mongodb-digital-services | digital-services-dev |  | 4- Low | 3
crypto | crypto-consumer, crypto | mongodb-digital-security-services | digital-security-services-dev | 21504 | 3 - Medium | 4
iamSaml | iam-saml-integration | mongodb-digital-security-services | digital-identity-services-dev | 1 | 3 - Medium | 4
notification | notification, notification-settings | mongodb-digital-services | digital-product-services-dev | 2048 | 3 - Medium | 4
marketingAutomation | marketing-builder,marketing-consumer | mongodb-account-iam | digital-account-services-dev | 2048 | 3 - Medium | 4
emailValidation | email-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 8192 | 2- Critical | 5
phoneValidation | phone-validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 647 | 2- Critical | 5
validation | validation | mongodb-digital-kyc-services | digital-kyc-services-dev | 8 | 2- Critical | 5
vault | vault | mongodb-digital-security-services | digital-security-services-dev |  | 2- Critical | 6
leadinfo | enrichment | mongodb-account-iam | digital-account-services-dev | 36864 | 2- Critical | 6
emailCommunication | email-communication | mongodb-digital-services | digital-communication-services-dev |  | 2- Critical | 7
sendgrid | email-communication-webhook, sendgrid, vault | mongodb-digital-services | digital-communication-services-dev | 32768 | 2- Critical | 7
sms | sms, sms-webhook | mongodb-digital-services | digital-communication-services-dev | 230 | 2- Critical | 7
platform | product-platform | mongodb-digital-services | digital-product-services-dev | 102 | 1- Highly Critical | 8
productMenuSecurity | product-menu-security | mongodb-digital-services | digital-product-services-dev | 182 | 1- Highly Critical | 8
switching | switching | mongodb-digital-services | digital-product-services-dev | 51 | 1- Highly Critical | 8
device | device | mongodb-digital-security-services | digital-security-services-dev | 1654982 | 1- Highly Critical | 9
drive | drive, drive-transfer | mongodb-digital-services | digital-storage-services-dev | 9665 | 1- Highly Critical | 9
product | product-access | mongodb-digital-services | digital-product-services-dev | 4242 | 1- Highly Critical | 9
account | account, account-event-payload, account-webhook, organization-structure, services-account | mongodb-account-iam | digital-account-services-dev | 222747 | 1- Highly Critical | 10
iam | iam, iam-batch, iam-event-payload, iam-legacy, identity-migration | mongodb-account-iam | digital-identity-services-dev | 3595350 | 1- Highly Critical | 11
catalogue | catalogue | mongodb-digital-commerce-services |  | 1 | 2- Critical | PME - DocumentDB
checkout | checkout-management | mongodb-digital-commerce-services |  | 820 | 4- Low | PME - DocumentDB
marketingcampaign | marketing-campaign | mongodb-digital-commerce-services |  | 7064 | 2- Critical | PME - DocumentDB
orderbalance | order-balance | mongodb-digital-commerce-services |  | 5060 | 2- Critical | PME - DocumentDB
orderBalanceWebhook | order-balance-webhook | mongodb-digital-commerce-services |  | 1 | 3 - Medium | PME - DocumentDB
ordersession | order-session-batch, order-session-management, order-session-notification-consumer | mongodb-digital-commerce-services |  | 96256 | 2- Critical | PME - DocumentDB
orderSessionWebhook | order-session-webhook | mongodb-digital-commerce-services |  | 565 | 2- Critical | PME - DocumentDB
payment | payment | mongodb-digital-commerce-services |  | 1 | 2- Critical | PME - DocumentDB
quartz | order-session-batch | mongodb-digital-commerce-services |  | 7168 | 3 - Medium | PME - DocumentDB
salesFraudScreening | fraud-screening-job, sales-fraud-screening | mongodb-digital-commerce-services |  | 168245 | 2- Critical | PME - DocumentDB
shoppingcart | shopping-cart-management | mongodb-digital-commerce-services |  | 2582 | 4- Low | PME - DocumentDB
showcase | showcase-management | mongodb-digital-commerce-services |  | 888788 | 2- Critical | PME - DocumentDB

## Mongo > Atlas - UAT
Database | Apps (experian-*-domain-services/webhook) | Target Digital EC2 cluster | Actual Volume (MB) | Business criticality | Ordem | Ordem Nova | Data UAT | Data Prod | Change
kba | kba | mongodb-digital-kyc-services | 3 | 4- Low | 1 |  | 2023-07-28 | 2023-08-14 | CHG1537578
personValidation | person-validation | mongodb-digital-kyc-services | 37 | 4- Low | 1 |  | 2023-07-28 | 2023-08-14 | CHG1537578
verifyid | verifyid | mongodb-digital-kyc-services | 46 | 4- Low | 1 |  | 2023-07-28 | 2023-08-14 | CHG1537578 | MÊS | DOM | SEG | TER | QUA | QUI | SEX | SAB
digitalCertificateWebhook | digital-certificate-webhook | mongodb-digital-security-services | 1 | 4- Low | 1 |  | 2023-07-28 | 2023-08-14 | CHG1537578 | JUL |  |  |  | 26 | 27 | 28 | 29
digitalKms | digital-kms | mongodb-digital-security-services | 1 | 4- Low | 1 |  | 2023-07-28 | 2023-08-15 | CHG1537578 | SEX: CHG1537578
adChanges | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | mongodb-digital-security-services | 8784 | 4- Low | 2 |  | 2023-07-28 | 2023-08-15 | CHG1537578 | AGO | 30 | 31 | 1 | 2 | 3 | 4 | 5
policy | policy, policy-settings | mongodb-digital-security-services | DESCONTINUADO | 4- Low | 2 |  | 2023-07-31 | 2023-08-16 |  |  | 31: CHG1543408; 1: CHG1558866; 2: CHG1559192; 3: CHG1569931
otp | otp | mongodb-digital-security-services | 897 | 4- Low | 2 |  | 2023-07-31 | 2023-08-16 | CHG1543408 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12
driveWebhook | driveWebhook | mongodb-digital-services | 1 | 4- Low | 2 |  | 2023-07-31 | 2023-08-16 | CHG1543408 | bar: 6; 11 to 12
healthcheck |  | mongodb-digital-services |  | 4- Low | 2 |  | 2023-07-31 | 2023-08-16 |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19
crypto | crypto-consumer, crypto | mongodb-digital-security-services | 21504 | 3 - Medium | 3 |  | 2023-07-31 | 2023-08-17 | CHG1543408 | bar: 13; 18 to 19
iamSaml | iam-saml-integration | mongodb-digital-security-services | 1 | 3 - Medium | 3 |  | 2023-08-01 | 2023-08-21 | CHG1558866 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26
notification | notification, notification-settings | mongodb-digital-services > mongodb-digital-product-services | 2048 | 3 - Medium | 3 |  | 2023-08-01 | 2023-08-17 | CHG1558866 | bar: 20; 25 to 26
marketingAutomation | marketing-builder,marketing-consumer | mongodb-account-iam | 2048 | 3 - Medium | 4 |  | 2023-08-01 | 2023-08-21 | CHG1558866 | SET | 27 | 28 | 29 | 30 | 31 | 1 | 2
emailValidation | email-validation | mongodb-digital-kyc-services | 8192 | 2- Critical | 4 |  | 2023-08-01 | 2023-08-21 | CHG1558866 | bar: 27; 1 to 2
phoneValidation | phone-validation | mongodb-digital-kyc-services | 647 | 2- Critical | 4 |  | 2023-08-01 | 2023-08-22 | CHG1558866 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9
validation | validation | mongodb-digital-kyc-services | 8 | 2- Critical | 4 |  | 2023-08-01 | 2023-08-22 | CHG1558866 | bar: 3; 8 to 9
vault | vault | mongodb-digital-security-services |  | 2- Critical | 5 |  | 2023-08-03 | 2023-08-22 | CHG1569931 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
leadinfo | enrichment | mongodb-account-iam | 36864 | 2- Critical | 5 |  | 2023-08-03 | 2023-08-22 | CHG1569931 | bar: 10; 15 to 16
emailCommunication | email-communication | mongodb-digital-services |  | 2- Critical | 5 |  | 2023-08-03 | 2023-08-23 | CHG1569931
sms | sms, sms-webhook | mongodb-digital-services | 230 | 2- Critical | 5 |  | 2023-08-03 | 2023-08-24 | CHG1569931
sendgrid | email-communication-webhook, sendgrid, vault | mongodb-digital-services | 32768 | 2- Critical | 5 |  | 2023-08-03 | 2023-08-23 | CHG1569931
platform | product-platform | mongodb-digital-services > mongodb-digital-product-services | 102 | 1- Highly Critical | 6 |  | 2023-08-07 | 2023-08-24 | CHG1581239
productMenuSecurity | product-menu-security | mongodb-digital-services > mongodb-digital-product-services | 182 | 1- Highly Critical | 6 |  | 2023-08-07 | 2023-08-24 | CHG1581239
switching | switching | mongodb-digital-services > mongodb-digital-product-services | 51 | 1- Highly Critical | 6 |  | 2023-08-07 | 2023-08-24 | CHG1581239
device | device | mongodb-digital-security-services | 1654982 | 1- Highly Critical | 6 |  | 2023-08-07 | 2023-09-02 | CHG1581239
drive | drive, drive-transfer | mongodb-digital-services | 9665 | 1- Highly Critical | 6 |  | 2023-08-07 | 2023-09-05 | CHG1581239
product | product-access | mongodb-digital-services > mongodb-digital-product-services | 4242 | 1- Highly Critical | 7 |  | 2023-08-08 | 2023-09-05 | CHG1581242
account | account, account-event-payload, account-webhook, organization-structure, services-account | mongodb-account-iam | 222747 | 1- Highly Critical | 7 |  | 2023-08-08 | 2023-09-04 | CHG1581242
iam | iam, iam-batch, iam-event-payload, iam-legacy, identity-migration | mongodb-account-iam | 3595350 | 1- Highly Critical | 7 |  | 2023-08-08 | 2023-09-02 | CHG1581242
catalogue | catalogue | mongodb-digital-commerce-services | 1 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
checkout | checkout-management | mongodb-digital-commerce-services | 820 | 4- Low | PME - DocumentDB |  |  |  | CHG1605199
marketingcampaign | marketing-campaign | mongodb-digital-commerce-services | 7064 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
orderbalance | order-balance | mongodb-digital-commerce-services | 5060 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
orderBalanceWebhook | order-balance-webhook | mongodb-digital-commerce-services | 1 | 3 - Medium | PME - DocumentDB |  |  |  | CHG1605199
ordersession | order-session-batch, order-session-management, order-session-notification-consumer | mongodb-digital-commerce-services | 96256 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
orderSessionWebhook | order-session-webhook | mongodb-digital-commerce-services | 565 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
payment | payment | mongodb-digital-commerce-services | 1 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
quartz | order-session-batch | mongodb-digital-commerce-services | 7168 | 3 - Medium | PME - DocumentDB |  |  |  | CHG1605199
salesFraudScreening | fraud-screening-job, sales-fraud-screening | mongodb-digital-commerce-services | 168245 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199
shoppingcart | shopping-cart-management | mongodb-digital-commerce-services | 2582 | 4- Low | PME - DocumentDB |  |  |  | CHG1605199
showcase | showcase-management | mongodb-digital-commerce-services | 888788 | 2- Critical | PME - DocumentDB |  |  |  | CHG1605199

## Mongo > Atlas - PROD
Data Prod | CHANGE | Database | Apps (experian-*-domain-services/webhook) | Target Digital EC2 cluster | Actual Volume (MB) | Business criticality | Ordem | Ordem Nova | Data UAT | Coluna1
2023-08-14 | CHG1616254 | kba | kba | mongodb-digital-kyc-services | 3 | 4- Low | 1 |  | 2023-07-27
2023-08-14 | CHG1616254 | personValidation | person-validation | mongodb-digital-kyc-services | 37 | 4- Low | 1 |  | 2023-07-27 |  | MÊS | DOM | SEG | TER | QUA | QUI | SEX | SAB
2023-08-14 | CHG1616254 | verifyid | verifyid | mongodb-digital-kyc-services | 46 | 4- Low | 1 |  | 2023-07-27 |  | JUL |  |  |  | 26 | 27 | 28 | 29
2023-08-14 | CHG1616254 | digitalCertificateWebhook | digital-certificate-webhook | mongodb-digital-security-services | DESCONTINUADO | 4- Low | 1 |  | 2023-07-27 | bar: MÊS to DOM; SEX to SAB
2023-08-14 | CHG1616254 | digitalKms | digital-kms | mongodb-digital-security-services | 1 | 4- Low | 1 |  | 2023-07-27 |  | AGO | 30 | 31 | 1 | 2 | 3 | 4 | 5
2023-08-14 | CHG1616254 | adChanges | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | mongodb-digital-security-services | 8784 | 4- Low | 1 |  | 2023-07-28 | bar: 30; 4 to 5
|  | policy | policy, policy-settings | mongodb-digital-security-services | DESCONTINUADO | 4- Low | 1 |  | 2023-07-28 |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12
2023-08-14 | CHG1616254 | otp | otp | mongodb-digital-security-services | 897 | 4- Low | 1 |  | 2023-07-31 | bar: 6; 11 to 12
2023-08-14 | CHG1616254 | driveWebhook | driveWebhook | mongodb-digital-services | 1 | 4- Low | 1 |  | 2023-07-31 |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19
2023-08-14 | CHG1616254 | healthcheck |  | mongodb-digital-services |  | 4- Low | 1 |  | 2023-07-31 | bar: 13; 15; 18 to 19
2023-08-14 | CHG1616254 | checkout | checkout-management | mongodb-digital-commerce-services | 820 | 4- Low | 1 |  |  |  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26
2023-08-14 | CHG1616254 | shoppingcart | shopping-cart-management | mongodb-digital-commerce-services | 2582 | 4- Low | 1 | bar: 20; 25 to 26
2023-08-17 | CHG1631617 | orderBalanceWebhook | order-balance-webhook | mongodb-digital-commerce-services | 1 | 3 - Medium | 2 |  |  |  | SET | 27 | 28 | 29 | 30 | 31 | 1 | 2
2023-08-17 | CHG1631617 | crypto | crypto-consumer, crypto | mongodb-digital-security-services | 21504 | 3 - Medium | 2 |  | 2023-07-31 | bar: 27; 1 to 2
2023-08-17 | CHG1631617 | notification | notification, notification-settings | mongodb-digital-services > mongodb-digital-product-services | 2048 | 3 - Medium | 2 |  | 2023-08-01 |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9
2023-08-17 | CHG1631617 | iamSaml | iam-saml-integration | mongodb-digital-security-services | 1 | 3 - Medium | 2 |  | 2023-08-01 | bar: 3; 8 to 9
2023-08-17 | CHG1631617 | marketingAutomation | marketing-builder,marketing-consumer (REVISAR CLUSTER DESTINO - mongodb-digital-iam) | mongodb-account-iam | 2048 | 3 - Medium | 2 |  | 2023-08-02 |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
2023-08-17 | CHG1631617 | logonPortal | logonPortal | mongodb-digital-product-services |  | 3 - Medium | 2 | bar: 10; 15 to 16
2023-08-21 | CHG1637410 | catalogue | catalogue | mongodb-digital-commerce-services | 1 | 2- Critical | 3 | bar: 10; 15 to 16
2023-08-21 | CHG1637410 | marketingcampaign | marketing-campaign | mongodb-digital-commerce-services | 7064 | 2- Critical | 3
2023-08-21 | CHG1637410 | leadinfo | enrichment (REVISAR CLUSTER DESTINO - mongodb-digital-iam) | mongodb-account-iam | 36864 | 2- Critical | 3 |  | 2023-08-03
2023-08-21 | CHG1637410 | emailCommunication | email-communication | mongodb-digital-services |  | 2- Critical | 3 |  | 2023-08-03
2023-09-04 | CHG1717621 | vault | vault | mongodb-digital-security-services |  | 2- Critical | 4 |  | 2023-08-03 |  | Freeze - Feriado São Carlos | bar: 10 to 11
2023-09-04 | CHG1717621 | emailValidation | email-validation | mongodb-digital-kyc-services | 8192 | 2- Critical | 4 |  | 2023-08-02
2023-09-04 | CHG1717621 | phoneValidation | phone-validation | mongodb-digital-kyc-services | 647 | 2- Critical | 4 |  | 2023-08-02
2023-09-04 | CHG1717621 | validation | validation | mongodb-digital-kyc-services | 8 | 2- Critical | 4 |  | 2023-08-02
2023-09-04 | CHG1717621 | sendgrid | email-communication-webhook, sendgrid, vault | mongodb-digital-services | 32768 | 2- Critical | 4 |  | 2023-08-07
2023-09-05 | CHG1717628 | orderbalance | order-balance | mongodb-digital-commerce-services | 5060 | 2- Critical | 5
2023-09-05 | CHG1717628 | orderSessionWebhook | order-session-webhook | mongodb-digital-commerce-services | 565 | 2- Critical | 5
2023-09-05 | CHG1717628 | payment | payment | mongodb-digital-commerce-services | 1 | 2- Critical | 5
2023-09-05 | CHG1717628 | salesFraudScreening | fraud-screening-job, sales-fraud-screening | mongodb-digital-commerce-services | 168245 | 2- Critical | 5
2023-09-11 | CHG1717632 | sms | sms, sms-webhook | mongodb-digital-services | 230 | 2- Critical | 6 |  | 2023-08-03
2023-09-11 | CHG1717632 | ordersession | order-session-batch, order-session-management, order-session-notification-consumer | mongodb-digital-commerce-services | 96256 | 2- Critical | 6
2023-09-13 | CHG1755028 | platform | product-platform | mongodb-digital-services > mongodb-digital-product-services | 102 | 1- Highly Critical | 7 |  | 2023-08-07
2023-09-13 | CHG1755028 | productMenuSecurity | product-menu-security | mongodb-digital-services > mongodb-digital-product-services | 182 | 1- Highly Critical | 7 |  | 2023-08-07
2023-09-13 | CHG1755028 | product | product-access | mongodb-digital-services > mongodb-digital-product-services | 4242 | 1- Highly Critical | 7
2023-09-12 | CHG1718075 | showcase | showcase-management | mongodb-digital-commerce-services | 888788 | 2- Critical | 8 |  |  | Transferido pra onda 7
2023-09-12 | CHG1718075 | drive | drive, drive-transfer | mongodb-digital-services | 9665 | 1- Highly Critical | 8
2023-09-12 | CHG1718075 | switching | switching | mongodb-digital-services > mongodb-digital-product-services | 51 | 1- Highly Critical | 8 |  | 2023-08-08
2023-09-12 | CHG1718075 | device | device | mongodb-digital-security-services | 1654982 | 1- Highly Critical | 8 |  | 2023-08-08
2023-09-19 | CHG1762060 | account | account, account-event-payload, account-webhook, organization-structure, services-account, account-migration | mongodb-account-iam | 222747 | 1- Highly Critical | 10 |  | 2023-08-10
2023-09-20 | CHG1827270 | quartz | order-session-batch | mongodb-digital-commerce-services |  | 3 - Medium | 11
2023-09-20 | CHG1827270 | driveWebhook | drive-webhook | mongodb-digital-services |  | 3 - Medium | 11
2023-10-09 | CHG1927186 | iam | iam, iam-batch, iam-event-payload, iam-legacy, identity-migration, certificate-domain-services, iamV2 | mongodb-account-iam (PME) > mongodb-digital-iam | 3595350 | 1- Highly Critical | 12 |  | 2023-08-11
|  | userAccessHistory | user-access-history-domain-service | mongodb-account-iam

## Endereços
Origem
docdb-digital-commerce-services | Terminated
docdb-digital-kyc-services | Terminated
docdb-digital-security-services | Terminated
docdb-digital-services | docdb-digital-services.cluster-cxuqnyyb34lr.sa-east-1.docdb.amazonaws.com | mongo --ssl --host docdb-digital-services.cluster-cxuqnyyb34lr.sa-east-1.docdb.amazonaws.com:27017 --sslCAFile rds-combined-ca-bundle.pem --username administrator --password <insertYourPassword>
docdb-docdb-account-services | Terminated
mongodb-account-iam | 10.97.55.13 | 10.97.55.59 | 10.97.55.178
mongodb-customer-relationship | 10.97.55.5 | 10.97.55.181 | 10.97.55.152
mongodb-digital-commerce-services | 10.97.55.105 | 10.97.55.70 | 10.97.55.89
mongodb-digital-services-crypto | Terminated
mongodb-persona-video-loan | Terminated
Target
mongodb-account-iam | 10.99.133.35 | 10.99.133.111 | 10.99.133.161
mongodb-digital-commerce-services | 10.99.133.26 | 10.99.133.84 | 10.99.133.163
mongodb-digital-kyc-services | 10.99.133.19 | 10.99.133.119 | 10.99.133.165
mongodb-digital-security-services | 10.99.133.10 | 10.99.133.106 | 10.99.133.147
mongodb-digital-services | 10.99.133.11 | 10.99.133.93 | 10.99.133.144
mongodb-digital-uat | 10.99.133.47 | 10.99.133.91 | 10.99.133.174

## Planilha2 (hidden)
| mongodb-account-iam | mongodb-digital-commerce-services | mongodb-digital-kyc-services | mongodb-digital-security-services | mongodb-digital-services | mongodb-digital-uat
docdb-digital-commerce-services
docdb-digital-kyc-services
docdb-digital-security-services
docdb-digital-services |  |  |  |  | platform, product, productMenuSecurity
docdb-docdb-account-services
mongodb-account-iam | account, iam |  |  | otp, digitalCertificateWebhook, adChanges, iamSaml
mongodb-customer-relationship |  |  | emailValidation | device | sms, drive, switching
mongodb-digital-commerce-services |  | orderBalanceWebhook, quartz, ordersession, marketingcampaign, orderbalance, orderSessionWebhook, checkout, shoppingcart, payment, salesFraudScreening, showcase
mongodb-digital-services-crypto
mongodb-persona-video-loan

## CHGxCUSTOS (hidden)
CHG | Data | Bases migradas | Criticidade | Porquê? | Clusters desativados | Resultado | Observações
CHG0950292 | 2023-04-11 | sendgrid, catalogue e marketingAutomation | Alta | sendgrid | mongodb-persona-videoloan (EC2), docdb-account-services e docdb-commerce-services | Sucesso | Erros 429 e findById existentes antes da CHG
CHG0966504 | 2023-04-12 | validation, kba, policy, digitalKms | Média | validation | docdb-kyc-services e docdb-security-services | Sucesso | CHG da app validation cancelada por conta do conflito
CHG0966801 | 2023-04-13 | checkout, shoppingcart, platform | Média | platform |  | Cancelada
CHG0969942 | 2023-04-17 | platform, adChanges, driveWebhook | Alta | platform |  | Cancelada
CHG0987840 | 2023-04-18 | personValidation, verifyId, notification, driveWebhook | Alta | personValidation |  | Sucesso
CHG0990489 | 2023-04-19 | crypto, phoneValidation, leadInfo | Alta | crypto | mongodb-services-crypto (EC2) | Sucesso
CHG0998516 | 2023-04-24 | platform, otp, quartz, orderBalanceWebhook | Alta | platform |  | Sucesso
CHG0998544 | 2023-04-25 | emailValidation, ordersession, sms, digitalCertificateWebhook, emailCommunication, emailCommunicationWebhook | Alta | emailValidation |  | Sucesso | emailCommunication criado e atribuído a app, emailCommunicationWebhook migrado do sendgrid
CHG1012530 | 2023-04-26 | product, adChanges, marketingcampaign, iamSaml, productMenuSecurity, vault | Alta | product | docdb-digital-services | Sucesso | adChanges possui views o que impediu de ser migrada usando o DMS, foi feito dump/restore e pausadas as 3 apps
CHG1012546 | 2023-04-27 | drive, switching, orderbalance, orderSessionWebhook, healthcheck | Alta | drive |  | Sucesso
CHG1027724 | 2023-05-02 | payment, checkout, shoppingcart, salesFraudScreening, showcase | Média | salesFraudScreening | mongodb-commerce-services (EC2) | Concluída | Base showcase foi abortada pelo tamanho exceder a janela de execução
CHG1055097 | 2023-05-03 | account, device | Alta | account | mongodb-customer-relationship (EC2) | Abortada | Erros na migração das bases account e device
| 2023-05-04 | iam | Média | iam | mongodb-account-iam (EC2)
CHG1095220 | 2023-05-10 | device, showcase | Alta | device | mongodb-customer-relationship (EC2), mongodb-commerce-services (EC2) | Em aprovação

## CALENDÁRIO DE MUDANÇAS
| DOM | SEG | TER | QUA | QUI | SEX | SAB
Abril | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | sendgrid, catalogue e marketingAutomation | validation, kba, policy, digitalKms | checkout, shoppingcart, platform
| 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | platform, adChanges, driveWebhook | personValidation, verifyId, notification, driveWebhook | crypto, phoneValidation, leadInfo |  | FERIADO
| 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | platform, otp, quartz, orderBalanceWebhook | emailValidation, ordersession, sms, digitalCertificateWebhook | product, adChanges, marketingcampaign, iamSaml, productMenuSecurity | drive, switching, orderbalance, orderSessionWebhook
Maio | 30 | 1 | 2 | 3 | 4 | 5 | 6
|  | FERIADO | payment, checkout, shoppingcart, salesFraudScreening, showcase | account, device | iam
| 7 | 8 | 9 | 10 | 11 | 12 | 13
showcase, device
| 14 | 15 | 16 | 17 | 18 | 19 | 20
| 21 | 22 | 23 | 24 | 25 | 26 | 27
| 28 | 29 | 30 | 31
Note on D6: Daud, Gustavo: CHG0950392