## CLUSTER DOCUMENT DB
Database | Apps (experian-*-domain-services/webhook) | App com certificado OK | Source Cluster | Target Cluster | Actual Volume (MB) | Business criticality | Status | Obs | Data Migração | Owner Migração | Tech Lead
account | account, account-event-payload, account-webhook, organization-structure, services-account | No | account-iam | account-iam | 173056 | Highly Critical | Not Migrated
iam | iam-batch, iam-event-payload, iam-legacy, identity-migration | No | account-iam | account-iam | 3145728 | Highly Critical | Not Migrated
leadinfo | enrichment, lead-enrichment-batch | No | customer-relationship | account-iam | 36864 | Critical | Not Migrated | Verificar nome mais semantico / lead-enrichment-batch não é feito deploy, alterar uri do job no Rundeck
mkt-automation |  |  | mkt-automation | account-iam | 2048 | Medium | Migrated
callcenter |  |  | customer-relationship | backup to Glacier and delete | 324 | Medium | Migrated |  | 2022-08-31 | Daud
dacourses |  |  | digital-commerce-services | backup to Glacier and delete |  | - | Migrated
userqrcode |  |  | customer-relationship | backup to Glacier and delete |  | - | Migrated |  | 2022-08-31 | Daud
wallet | wallet | Yes | customer-relationship | backup to Glacier and delete | 47 | Low | Migrated
consultafacil |  |  | digital-commerce-services | delete |  | - | Migrated
consultafacilreports |  |  | digital-commerce-services | delete |  | - | Migrated
consultafacilsecurity |  |  | digital-commerce-services | delete |  | - | Migrated
iamlegacy |  |  | customer-relationship | delete |  | - | Migrated
partner |  |  | account-iam | delete |  | Low | Migrated | DELETAR
verifyId |  |  | account-iam | delete |  | - | Migrated
catalogue | catalogue | Yes | customer-relationship | digital-commerce-services | 1 | Critical | Migrated |  | 2022-09-05 | Daud
checkout | checkout-management | Yes | digital-commerce-services | digital-commerce-services | 820 | Low | Not Migrated
marketingcampaign | marketing-campaign | Yes | digital-commerce-services | digital-commerce-services | 5120 | Critical | Not Migrated
orderbalance | order-balance | Yes | digital-commerce-services | digital-commerce-services | 98 | Critical | Not Migrated
orderBalanceWebhook | order-balance-webhook | Yes | digital-commerce-services | digital-commerce-services | 1 | Medium | Not Migrated
ordersession | order-session-batch, order-session-management, order-session-notification-consumer | No | digital-commerce-services | digital-commerce-services | 96256 | Critical | Not Migrated
orderSessionWebhook | order-session-webhook | Yes | digital-commerce-services | digital-commerce-services | 540 | Critical | Not Migrated
payment | payment | Yes | digital-commerce-services | digital-commerce-services | 2048 | Critical | Not Migrated
quartz | order-session-batch | No | digital-commerce-services | digital-commerce-services | 7168 | Medium | Not Migrated
salesFraudScreening | fraud-screening-job, sales-fraud-screening | No | digital-commerce-services | digital-commerce-services | 109568 | Critical | Not Migrated
shoppingcart | shopping-cart-management | Yes | digital-commerce-services | digital-commerce-services | 2048 | Low | Not Migrated
showcase | showcase-management | Yes | digital-commerce-services | digital-commerce-services | 568320 | Critical | Not Migrated
emailValidation | email-validation | Yes | customer-relationship | digital-kyc-services | 8192 | Critical | Not Migrated |  | 2022-09-19 | Daud | Ricardo Neves
kba | kba | Yes | customer-relationship | digital-kyc-services | 3 | Low | Migrated |  | 2022-09-08 | Eduardo | Ricardo Neves
personValidation | person-validation | Yes | customer-relationship | digital-kyc-services | 37 | Low | Not Migrated |  | 2022-09-13 | André | Victor Zanin
phoneValidation | phone-validation | Yes | customer-relationship | digital-kyc-services | 647 | Critical | Not Migrated |  | 2022-09-20 | Wellington | Marco Barbosa
validationDomain | validation | Yes | customer-relationship | digital-kyc-services | 8 | Critical | Migrated | Renomeado para validation | 2022-09-12 | Wellington | Marco Barbosa
verifyid | verifyid | Yes | customer-relationship | digital-kyc-services | 46 | Low | Not Migrated |  | 2022-09-14 | Davi | Lombardi
adChanges | ad-changes, ad-changes-consumer, ad-gerenciador-mapping | No | account-iam | digital-security-services | 5120 | Low | Not Migrated
crypto | crypto-consumer, crypto | No | digital-services-crypto | digital-security-services | 21504 | Medium | Not Migrated
device | device | Yes | customer-relationship | digital-security-services | 918528 | Highly Critical | Not Migrated |  | 2022-09-16 | Cunha | Lombardi
digitalCertificateWebhook | digital-certificate-webhook | Yes | account-iam | digital-security-services | 1 | Low | Not Migrated
digitalKms |  |  | customer-relationship | digital-security-services | 1 | Low | Migrated
iamSaml | iam-saml-integration | Yes | account-iam | digital-security-services | 1 | Medium | Not Migrated
otp | otp | Yes | account-iam | digital-security-services | 897 | Low | Not Migrated
policy |  |  | customer-relationship | digital-security-services | 1 | Low | Migrated
drive | drive, drive-transfer | No | customer-relationship | digital-services | 7168 | Highly Critical | Not Migrated
driveWebhook | driveWebhook | Yes | customer-relationship | digital-services | 1 | Low | Migrated | Base vazia, só criar a base no document e mudar a string
emailCommunication |  |  | customer-relationship | digital-services |  | Critical | Migrated
notification |  |  | digital-notification | digital-services | 2048 | Medium | Migrated
plataform | product-platform | Yes | digital-products | digital-services | 102 | Highly Critical | Migrated |  | 2022-08-29 | Cunha/André
product | product-access | Yes | digital-products | digital-services | 2328 | Highly Critical | Migrated |  | 2022-08-29 | Cunha/André
sendgrid | email-communication-webhook, sendgrid | Yes | persona-video-loan | digital-services | 32768 | Critical | Not Migrated |  | 2022-09-21 | Eduardo | Victor Zanin
sms | sms, sms-webhook | Yes | customer-relationship | digital-services | 230 | Critical | Not Migrated |  | 2022-09-15 | Eduardo | Ricardo Neves
switching | switching | No | customer-relationship | digital-services | 51 | Highly Critical | Not Migrated | Validar indices das collection | 2022-08-29 | Cunha/André

## EKS NAMESPACE
Migração EKS
Status | Application | Openshift Namespace | EKS Namespace | Observação
| experian-enrichment-domain-services | digital-services | digital-account-services
| experian-lead-enrichment-batch-services | digital-services | digital-account-services
| experian-leads-dw-domain-services | digital-services | digital-account-services
| experian-account-domain-services | digital-services-account | digital-account-services
| experian-account-event-payload-domain-services | digital-services-account | digital-account-services
| experian-account-migration-domain-services | digital-services-account | digital-account-services
| experian-account-webhook-domain-services | digital-services-account | digital-account-services
| experian-integration-account-dispatch-domain-services | digital-services-account | digital-account-services
| experian-organizational-structure-domain-services | digital-services-account | digital-account-services
| experian-service-account-domain-services | digital-services-account | digital-account-services
ok | experian-marketing-automation-builder | mkt-automation | digital-account-services
ok | experian-marketing-automation-consumer | mkt-automation | digital-account-services
| experian-catalogue-domain-services | digital-services | digital-commerce-services
| experian-wallet-domain-services | digital-services | digital-commerce-services
| experian-checkout-management-domain-services | seef-prd | digital-commerce-services
| experian-digital-commerce-spring-boot-admin | seef-prd | digital-commerce-services
| experian-fraud-screening-job | seef-prd | digital-commerce-services
| experian-invoice-domain-services | seef-prd | digital-commerce-services
| experian-marketing-campaign-domain-services | seef-prd | digital-commerce-services
| experian-order-balance-domain-services | seef-prd | digital-commerce-services
| experian-order-balance-webhook | seef-prd | digital-commerce-services
| experian-order-session-batch-domain-services | seef-prd | digital-commerce-services
| experian-order-session-management-domain-services | seef-prd | digital-commerce-services
| experian-order-session-notification-consumer | seef-prd | digital-commerce-services
| experian-order-session-webhook | seef-prd | digital-commerce-services
| experian-payment-domain-services | seef-prd | digital-commerce-services
| experian-sales-fraud-screening-domain-services | seef-prd | digital-commerce-services
| experian-shopping-cart-management-domain-services | seef-prd | digital-commerce-services
| experian-showcase-management-domain-services | seef-prd | digital-commerce-services
| experian-email-communication-domain-services | digital-services | digital-communication-services
| experian-email-communication-webhook | digital-services | digital-communication-services
| experian-sendgrid-domain-services | digital-services | digital-communication-services
| experian-sms-dispatch-domain-services | digital-services | digital-communication-services
| experian-sms-domain-services | digital-services | digital-communication-services
| experian-sms-webhook | digital-services | digital-communication-services
| experian-iam-batch | digital-services-identity | digital-identity-services
| experian-iam-domain-services | digital-services-identity | digital-identity-services
| experian-iam-event-payload-domain-services | digital-services-identity | digital-identity-services
| experian-iam-legacy-domain-services | digital-services-identity | digital-identity-services
| experian-iam-saml-integration-domain-services | digital-services-identity | digital-identity-services
| experian-identity-migration-domain-services | digital-services-identity | digital-identity-services
| experian-integration-iam-dispatch-domain-services | digital-services-identity | digital-identity-services
| experian-digital-certificate-webhook | digital-services-identity | digital-identity-services
ok | experian-email-validation-domain-services | digital-services | digital-kyc-services
ok | experian-phone-validation-domain-services | digital-services | digital-kyc-services
ok | experian-validation-domain-services | digital-services | digital-kyc-services
| experian-kba-domain-services | digital-services-kyc | digital-kyc-services
| experian-person-validation-domain-services | digital-services-kyc | digital-kyc-services
| experian-verifyid-domain-services | digital-services-kyc | digital-kyc-services
| experian-switching-domain-services | digital-services | digital-product-services
| experian-notification-domain-services | digital-services-notification | digital-product-services
| experian-notification-settings-domain-services | digital-services-notification | digital-product-services
| experian-product-access-domain-services | digital-services-product | digital-product-services
| experian-product-platform-domain-services | digital-services-product | digital-product-services
| experian-ad-changes | digital-services-identity | digital-security-services
| experian-ad-changes-consumer | digital-services-identity | digital-security-services
| experian-ad-gerenciador-mapping-domain-services | digital-services-identity | digital-security-services
| experian-otp-domain-services | digital-services-identity | digital-security-services
| experian-policy-domain-services | digital-services-identity | digital-security-services
| experian-policy-settings-domain-services | digital-services-identity | digital-security-services
| experian-account-backoff | digital-services | digital-security-services | Verificar possibilidade de alterar o nome da aplicação
| experian-device-domain-services | digital-services | digital-security-services
| experian-vault-domain-services | digital-services | digital-security-services
| experian-crypto-consumer-domain-services | digital-services-crypto | digital-security-services
| experian-crypto-domain-services | digital-services-crypto | digital-security-services
ok | experian-kms-domain-services | digital-data-security | digital-security-services
| experian-drive-domain-services | digital-services | digital-storage-services
| experian-drive-transfer-domain-services | digital-services | digital-storage-services
| experian-drive-webhook | digital-services | digital-storage-services
| experian-identity-provider-frontend | digital-services-identity | S3 Migration
| experian-product-menu | digital-services-identity | S3 Migration
| experian-dasp-frontend | digital-services | S3 Migration
| manuais-e-treinamentos | digital-services-frontend | S3 Migration
ok | experian-drive-v2 | digital-services | digital-storage-services
| experian-account-backoffice-frontend | digital-services | digital-security-services
| experian-call-center-domain-services | digital-services | digital-account-services
| experian-digital-organizational-structure-domain-services | digital-services-account | digital-account-services
ok | experian-drive-transfer-v2-domain-services | digital-services | digital-storage-services
| experian-email-communication-domain-services | digital-services | digital-communication-services
ok | experian-lead-enrichment-batch-services | digital-services | delete | Não há necessidade de migrar, library usada no Rundeck
| experian-leads-dw-domain-services | digital-services | digital-account-services
9 | 81 | 11.11% | Concluídos

## AMAZON MQ VIRTUAL HOSTS
Migração RabbitMQ
Status | Queue | Source RabbitMQ Cluster | Target Amazon MQ - Virtual Hosts (Unique Cluster) | Observação
| EmailValidationQueue | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| adchanges-messages | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| digital-certificate-event | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| digital-certificate-event-dispatch | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| digital-certificate-event-dispatch-dlq | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| digital-certificate-event-dlq | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /security
| dispatch-iam | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /identity
| event-iam | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /identity
| dispatch-account | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /account
| dispatch-account-dlq | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /account
| event-account | rabbit@ip-10-97-55-141.sa-east-1.compute.internal | /account
| dispatch-order-session | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | delete
| event-order-session | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | delete
| event-third-party-order-process | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| event-third-party-order-process-wait | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| event-third-party-orders-process | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-balance-event | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-balance-event-dispatcher | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-balance-event-dispatcher-dlq | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-balance-event-dlq | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-session-event | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-session-event-dispatcher | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-session-event-dispatcher-dlq | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| order-session-event-dlq | rabbit@ip-10-97-55-243.sa-east-1.compute.internal | /e-commerce
| mkt-automation | Not found | /account
| event-crypto | rabbit@ip-10-97-55-123.sa-east-1.compute.internal | /security
| drive-event | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /storage
| drive-event-dispatcher | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /storage
| drive-event-dispatcher-dlq | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /storage
| drive-event-dlq | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /storage
| email-communication-event | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication
| email-communication-event-dispatch | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication
| email-communication-event-dispatch-dlq | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication
| email-communication-event-dlq | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication
| sms-messages | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication
| sms-messages-callback | rabbit@ip-10-97-55-11.sa-east-1.compute.internal | /communication

## MONGODB ISSUE PLANNING
| DOM | SEG | TER | QUA | QUI | SEX | SAB
Ago | 21 | 22 | 23 | 24 | 25 | 26 | 27
|  |  | notification |  |  |  |  | (1) 918GB, tempo estimado de 24-36h
Set | 28 | 29 | 30 | 31 | 1 | 2 | 3
|  | platform product crypto |  | callcenter leadinfo
| 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | wallet catalogue |  |  | verifyId personValidation kba
| 11 | 12 | 13 | 14 | 15 | 16 | 17
|  | emailValidation phoneValidation |  | validationDomain driveWebhook sms |  | device(1)
| 18 | 19 | 20 | 21 | 22 | 23 | 24
drive
Out | 25 | 26 | 27 | 28 | 29 | 30 | 1
switching
| 2 | 3 | 4 | 5 | 6 | 7 | 8
| 9 | 10 | 11 | 12 | 13 | 14 | 15
| 16 | 17 | 18 | 19 | 20 | 21 | 22
| 23 | 24 | 25 | 26 | 27 | 28 | 29
Nov | 30 | 1 | 2 | 3 | 4 | 5 | 6
| 7 | 8 | 9 | 10 | 11 | 12 | 13
| 14 | 15 | 16 | 17 | 18 | 19 | 20
| 21 | 22 | 23 | 24 | 25 | 26 | 27
| 28 | 29 | 30

## Planilha1
experian-identity-migration-domain-services
experian-ad-changes-consumer